## SH Register
| Project Name | "VNS" – Custom University Learning Platform | Date | 24/09/2026
| Project Manager | Nazar Zankovych | Version | V1.0
| Project Sponsor | Lviv Polytechnic National University; Ministry of Education and Science of Ukraine | Project Start Date | 22/09/2026
| Project Phase | Initiation | Project End Date | 31/01/2027
|  |  | Author | Andrii Lysun (Business Analyst)
STAKEHOLDERS | Name | Category | Organization | Role/Job Title | Email | Phone | Communication Channel | Frequency | Location | Time Zone | Power* | Interest* | Approach* | Comments/Notes
| Full name of the stakeholder | Internal / External / Primary or Secondary | The name of the organization or group the stakeholder belongs to | Job title or role held by the stakeholder | Work Email and personal Email, with consent of individual | Primary + alternative contact info | Via email, Conference call, Message etc. | The frequency of communication to be done within a pre-defined timeframe | City and Country where the person is located | Time Zone which the person belongs to | High / Low | High / Low | Key Player / Keep Informed / Meet their needs etc. | Additional details to keep in mind
| Lviv Polytechnic National University | External / Primary | Lviv Polytechnic National University | Project Sponsor, owner of the future platform | office@lpnu.ua | +380 (32) 258-21-11 | Status meeting + written report | Every second Tuesday | Lviv, Ukraine | EET (UTC+2) | High | High | Key Player | Funds the project, owns the current VNS and the student data, accepts the final result.
| Ministry of Education and Science of Ukraine | External / Secondary | Ministry of Education and Science of Ukraine | Sector regulator, formal co-sponsor | office@mon.gov.ua | +380 (44) 481-32-21 | No regular communication | Only if regulation changes | Kyiv, Ukraine | EET (UTC+2) | Low | Low | Monitor | No influence on a one-department pilot. Monitored only; no RACI column and no recurring meetings.
| Nataliia Shakhovska | External / Primary | Rector's Office, Lviv Polytechnic National University | Rector (Executive Sponsor) | nataliia.b.shakhovska@lpnu.ua | +380 (32) 258-26-00 | E-mail with a one-page summary | Once per semester + milestones | Lviv, Ukraine | EET (UTC+2) | High | Low | Meet their needs | Signs the project charter and decides on scaling beyond the pilot. Summary level only.
| Nataliia Boiko | External / Primary | Lviv Polytechnic National University | Lecturer – customer and end user | nataliia.i.boiko@lpnu.ua | +380 (32) 258-25-30 | Interview, workshop, demo | Every Thursday | Lviv, Ukraine | EET (UTC+2) | High | High | Key Player | Defines and accepts the lecturer requirements and will use the product herself.
| Technical Department of Lviv Polytechnic | External / Primary | Lviv Polytechnic National University | Developers and administrators of the current VNS | it.support@lpnu.ua | +380 (32) 258-21-77 | Working meeting + e-mail | Every two weeks | Lviv, Ukraine | EET (UTC+2) | High | High | Key Player | Own the infrastructure and the student registry. Risk of resistance: engage them as partners.
| Students of Lviv Polytechnic | External / Primary | Student body of Lviv Polytechnic National University | End users of the platform | via @lpnu.ua mailboxes | — | Surveys, usability tests | Weekly during the pilot | Lviv, Ukraine | EET (UTC+2) | Low | High | Keep Informed | No say in decisions, but every requirement is validated with them.
| Kostiantyn Holovskyi | Internal / Primary | Project team “20/80” | Product Owner | kostiantyn.holovskyi.shi.2025@lpnu.ua | +380 (67) 000-00-01 | Planning meeting + backlog | Every Monday | Lviv, Ukraine | EET (UTC+2) | High | High | Key Player | Owns the product vision, the MVP scope and the backlog priorities.
| Nazar Zankovych | Internal / Primary | Project team “20/80” | Project Manager | nazar.zankovych.shi.2025@lpnu.ua | +380 (67) 000-00-02 | All project meetings | Daily | Lviv, Ukraine | EET (UTC+2) | High | High | Key Player | Plan, schedule, communications; single contact for the sponsors.
| Andrii Lysun | Internal / Primary | Project team “20/80” | Business Analyst | andrii.lysun.shi.2025@lpnu.ua | +380 (67) 000-00-03 | Elicitation meetings, workshops | Weekly + on demand | Lviv, Ukraine | EET (UTC+2) | High | High | Key Player | Elicits and documents requirements, owns the BA artifacts and UML models.
| Denys Lunhul | Internal / Primary | Project team “20/80” | Tech Lead | denys.lunhul.shi.2025@lpnu.ua | +380 (67) 000-00-04 | Technical sync + code review | Every Tuesday | Lviv, Ukraine | EET (UTC+2) | High | High | Key Player | Backend architecture, data model and technology stack decisions.
| Yaroslav Shevchuk | Internal / Secondary | Project team “20/80” | DevOps | yaroslav.shevchuk.shi.2025@lpnu.ua | +380 (67) 000-00-05 | Daily stand-up | Daily | Lviv, Ukraine | EET (UTC+2) | Low | High | Keep Informed | Environments, CI/CD and workers for AI tasks; works with the Tech Department.
| Volodymyr Kamelchuk | Internal / Secondary | Project team “20/80” | QA Specialist | volodymyr.kamelchuk.shi.2025@lpnu.ua | +380 (67) 000-00-06 | Daily stand-up + defect report | Daily | Lviv, Ukraine | EET (UTC+2) | Low | High | Keep Informed | Checks acceptance criteria, the grade forecast and the AI refusal rules.

## RACI
Legend: | R | Responsible
| A | Accountable
| C | Consulted
| I | Informed
Phase | Role | Rector (Exec. Sponsor) | Sponsor (LPNU) | Product Owner | Project Manager | Business Analyst | Tech Lead | DevOps | Quality Assurance | Customer (N. Boiko) | Tech Department | Students
Activity
Initiation | Audit the current VNS, agree the problem | I | A | R | R | R | C | I | I | C | C | C
| Identify and analyse stakeholders | I | C | C | A | R | I | I | I | C | I | I
| Choose a custom backend over Moodle | I | A | R | C | C | R | C | I | C | C | I
| Develop the business case | I | C | A | R | R | C | I | I | C | I | I
| Approve the project charter and MVP scope | A | C | R | R | C | C | I | I | C | I | I
Planning | Elicit requirements and build UML models |  | I | C | C | R/A | C | I | C | C | C | C
| Design the data model and architecture |  | I | C | C | C | R/A | R | C | I | C
| Select the tech stack and LLM API provider | I | C | C | C | C | A | R | C | I | C
| Approve student data use and LLM API access | C | A | C | R | R | C | C | I | C | C | I
| Create the schedule and communication plan | I | C | C | R/A | R | C | C | C | C | I | I
Execution | Registration via the student registry |  | C | C | C | C | A | R | C | I | R | I
| Courses, deadlines, grade forecast |  | I | C | I | C | R/A | I | C | C | I | I
| Communication hub and Study Spaces |  | I | C | I | C | R/A | R | C | C | I | C
| AI assistant: summaries, quizzes, Q&A |  | I | A | I | C | R | R | C | C | I | C
| Environments and CI/CD |  | I | I | I | I | C | R/A | C |  | C
| Testing and acceptance checks |  | I | C | C | C | C | C | R/A | C | I | C
Control | Manage scope changes and backlog | I | C | A | R | R | C | I | I | C | I | I
| Monitor LLM API costs and quotas | I | C | C | R/A | I | C | R |  |  | I
| Report status to sponsors | I | I | C | R/A | R | C | I | C | I | I | I
Close | Run the student pilot, collect feedback | I | C | A | R | R | C | C | C | R | C | R
| Hand over the system and documentation | C | C | R | A | R | R | R | C | C | R | I
| Capture lessons learned, close project | I | C | C | A | R | C | C | C | C | C | I

## SH Matrix
low POWER high | SATISFY |  |  |  | ENGAGE
|  | Nataliia Shakhovska Rector | Lviv Polytechnic (Project Sponsor) | Nataliia Boiko Customer |  | Technical Department
|  |  | Product Owner K. Holovskyi | Project Manager N. Zankovych |  | Business Analyst A. Lysun
Tech Lead D. Lunhul
| MONITOR |  |  |  | INFORM
|  | Ministry of Education and Science | Students (End users) | DevOps Y. Shevchuk |  | QA Specialist V. Kamelchuk
low INTEREST high