## Stakeholder register
Stakeholder Register
Project Name | "VNS" — Custom University Learning Platform |  |  |  |  | Date | 02/10/2026
Project Manager | Nazar Zankovych (nazar.zankovych.shi.2025@lpnu.ua) |  |  |  |  | Version | V1.2
Project Sponsor | Lviv Polytechnic National University; Ministry of Education and Science of Ukraine |  |  |  |  | Project Start Date | 22/09/2026
Project Phase | Initiation |  |  |  |  | Project End Date | 31/01/2027
Author | Andrii Lysun (Business Analyst) |  |  |  |  | Status | Draft for team approval
Stakeholder Name | Category | Stakeholder Group | Organization or Group | Role or Job title | Power/Influence | Interest | Address | Phone number | Email address | Preferable way of communication | Frequency of Communication | Comments and notes
Full name of the stakeholder | Internal / External / Primary or Secondary | Key Player / Keep Informed / Meet their needs etc | The name of the organization or group the stakeholder belongs to | Job title or role held by the stakeholder | High / Low | High / Low | Primary contact address | Primary + alternative contact info | Work Email and personal Email, with consent of individual | If phone, meetings or email | Record of letters, phone calls sent to stakeholder | Known contacts affiliations etc.
Lviv Polytechnic National University | External / Primary | Key Player | Lviv Polytechnic National University | Project Sponsor — customer and owner of the future platform | High | High | 12 S. Bandery Street, Lviv, 79013, Ukraine | +380 (32) 258-21-11 | office@lpnu.ua | Meeting + written status report | Every two weeks, Tuesday | Funds the project, owns the current VNS platform and the student data, and represents the university leadership: approves the project charter and MVP scope and accepts the final result. Main interest is replacing the outdated Moodle-based platform and gaining engagement analytics.
Ministry of Education and Science of Ukraine | External / Secondary | Meet their needs | Ministry of Education and Science of Ukraine | Project Sponsor — sector regulator and funding source | High | Low | 10 Peremohy Avenue, Kyiv, 01135, Ukraine | +380 (44) 481-32-21 | office@mon.gov.ua | Official one-page report | Once per semester and at control points | Sets the regulatory framework for educational IT systems and for processing personal data in education, and can condition the scaling of the product beyond the pilot. Not involved in day-to-day work: kept satisfied through formal semester reporting and consulted only on decisions with regulatory impact.
Technical Department of Lviv Polytechnic | External / Secondary | Monitor | Lviv Polytechnic National University | Developers and administrators of the current VNS | Low | Low | 12 S. Bandery Street, Lviv, 79013, Ukraine | +380 (32) 258-21-77 | it.support@lpnu.ua | E-mail / ticket on request | As needed (registry export, infrastructure access) | Built and maintain the current VNS. Because the project uses its own custom backend with no Moodle integration, the department neither controls delivery nor depends on its result. Involvement is limited to one-off requests: the export of the student registry and access to university infrastructure. Monitored in case they react to the replacement of their system.
End users — students and lecturers | External / Primary | Keep Informed | Students and teaching staff of Lviv Polytechnic National University | End users of the product: students and lecturers | Low | High | 12 S. Bandery Street, Lviv, 79013, Ukraine | — | Via learning channels and @lpnu.ua mailboxes | Interviews, surveys, usability tests, demos | Weekly during elicitation and the pilot | Primary target audience in two roles. Students: scattered chats, misleading grade summary, empty calendar. Lecturers: course materials, assignments, activity analytics and the AI mode for graded work. No direct influence on decisions, but requirements not validated with them will be wrong.
Kostiantyn Holovskyi | Internal / Primary | Key Player | Project team “20/80” | Product Owner | High | High | 5 Lukasha Street, Lviv, Ukraine | +380 (67) 000-00-01 | kostiantyn.holovskyi.shi.2025@lpnu.ua | Team meeting + backlog | Weekly, Monday | Owns the product vision and backlog priorities. Approves the MVP scope and accepts the result from the product side.
Nazar Zankovych | Internal / Primary | Meet their needs | Project team “20/80” | Project Manager | High | Low | 5 Lukasha Street, Lviv, Ukraine | +380 (67) 000-00-02 | nazar.zankovych.shi.2025@lpnu.ua | All project ceremonies | Daily | High authority over the plan, schedule, resources and communications. Interest is in delivering on time and within scope rather than in the functional content of the product, which is owned by the Product Owner. Single point of contact for the sponsors.
Andrii Lysun | Internal / Primary | Key Player | Project team “20/80” | Business Analyst | High | High | 5 Lukasha Street, Lviv, Ukraine | +380 (67) 000-00-03 | andrii.lysun.shi.2025@lpnu.ua | Requirements elicitation meetings, workshops | Weekly + as needed | Elicits and documents requirements and produces the BA artifacts and UML models. Main contact for the end users — both students and lecturers.
Denys Lunhul | Internal / Primary | Key Player | Project team “20/80” | Tech Lead, Software Engineer (SWE) | High | High | 5 Lukasha Street, Lviv, Ukraine | +380 (67) 000-00-04 | denys.lunhul.shi.2025@lpnu.ua | Technical sync + code review | Weekly, Tuesday | Software engineer who also leads the technical side: owns the custom backend architecture, decides on the technology stack and is accountable for the technical feasibility of requirements.
Yaroslav Shevchuk | Internal / Secondary | Monitor | Project team “20/80” | DevOps, Software Engineer (SWE) | Low | Low | 5 Lukasha Street, Lviv, Ukraine | +380 (67) 000-00-05 | yaroslav.shevchuk.shi.2025@lpnu.ua | Daily stand-up + technical sync | Daily | Software engineer who also owns deployment, environments and CI/CD. Low influence: executes tasks agreed in planning and does not set scope or priorities. Low interest in the business outcome: engagement is at task level. Kept in the loop through the team's own ceremonies, so no separate stakeholder communication is needed.
Volodymyr Kamelchuk | Internal / Secondary | Monitor | Project team “20/80” | QA Specialist, Software Engineer (SWE) | Low | Low | 5 Lukasha Street, Lviv, Ukraine | +380 (67) 000-00-06 | volodymyr.kamelchuk.shi.2025@lpnu.ua | Daily stand-up + defect report | Daily | Software engineer who also verifies the acceptance criteria, in particular the grade forecast and the AI's refusal to produce complete solutions for graded work. Low influence and low interest in the business outcome; kept in the loop through the team's own ceremonies.
LEGEND AND COMPLETION RULES
Category | Internal — a member of the delivery team; External — a stakeholder on the university or state side. Primary — directly involved; Secondary — involved indirectly.
Stakeholder Group | Derived from Power/Influence × Interest: High+High = Key Player (ENGAGE); High+Low = Meet their needs (SATISFY); Low+High = Keep Informed (INFORM); Low+Low = Monitor (MONITOR).
MONITOR quadrant | The Technical Department, DevOps and QA sit here. The department only handles one-off requests because the custom backend does not depend on the current VNS; DevOps and QA execute agreed tasks and are kept in the loop through the team's own ceremonies.
Contact details | Phone numbers are illustrative placeholders for this training project. Team e-mail addresses follow the real Lviv Polytechnic National University format.