## RACI Matrix
RACI Matrix — "VNS" — Custom University Learning Platform
Project Phase | Initiation |  |  | Version | V1.2 |  |  | Date | 02/10/2026 |  | Author | A. Lysun (BA), N. Zankovych (PM)
| Project Leadership |  |  | Project Team Members |  |  | Project Sub-Teams |  | External Resources
Project activity / deliverable | Lviv Polytechnic National University (Project Sponsor) | Ministry of Education and Science (Sponsor, regulator) | Product Owner (K. Holovskyi) | Project Manager (N. Zankovych) | Business Analyst (A. Lysun) | Tech Lead / SWE (D. Lunhul) | DevOps / SWE (Y. Shevchuk) | QA / SWE (V. Kamelchuk) | Technical Department of Lviv Polytechnic | End users — students and lecturers
Initiation Phase
- Agree on the problem statement and business context (audit of the current VNS) | A |  | R | R | R | C | I | I | I | C
- Identify and analyse stakeholders (register, power/interest matrix) | C |  | C | A | R | I | I | I |  | I
- Approve the strategy: custom backend instead of Moodle integration | A |  | R | C | C | R | C | I | I | I
- Develop the business case and the success metrics | C | C | A | R | R | C | I | I |  | I
- Approve the project charter and the MVP scope | A | C | R | R | C | C | I | I |  | I
Planning Phase
- Elicit and document requirements (interviews with lecturers, student surveys) | I |  | C | I | R/A | C | I | C |  | C
- Build UML models (use case, activity) for the product scenarios |  |  | C | I | R/A | C | I | C |  | I
- Design the data model and the custom backend architecture |  |  | C | I | C | R/A | R | C
- Approve processing of student personal data and transfer of materials to the LLM API | A | C | C | R | R | C | I | I | I | I
- Produce the communications plan and the project schedule | C |  | C | R/A | R | C | I | I
- Select the technology stack and the LLM API provider | C |  | C | C | I | A | R | C
Execution Phase
- Obtain the student registry; implement registration and authentication | C |  | C | I | C | R/A | R | R | R | I
- Implement courses, materials, deadlines and grade forecasting |  |  | C | I | C | R/A | R | R |  | C
- Implement the communication hub and Study Spaces |  |  | C | I | C | R/A | R | R |  | C
- Implement the AI assistant: summaries, quizzes, “Ask the course” | I |  | A | I | C | R | R | R |  | C
- Set up environments and configure CI/CD |  |  | I | I |  | A | R | C | C
- Run testing and acceptance checks |  |  | A | I | C | C | C | R |  | C
- Deploy the platform to the production environment | I |  | I | C | I | A | R | C | C | I
Control Phase
- Manage scope changes and backlog priorities | C |  | A | R | R | C | I | I |  | I
- Control quality, defects and adherence to the acceptance criteria |  |  | C | I | C | A | I | R |  | C
- Monitor LLM API costs, quotas and request limits | C |  | I: C; C: R/A; A: C; R: R
- Report project status to the sponsors | I | I | I: C; C: R/A; I: R; A: C
Close Phase
- Run the pilot with students and lecturers and collect feedback | C |  | A | R | R | C | C | C |  | R
- Hand over the system and documentation to the sponsor | C |  | R | A | R | R | R | C | I
- Capture lessons learned and close the project | I |  | C | A | R | C | C | C
LEGEND
R — Responsible | People or stakeholders who do the work. Several roles can be jointly Responsible.
A — Accountable | The owner of the work, who signs off or approves it when complete. Exactly one role is Accountable for each activity, and only roles with high influence are ever Accountable.
C — Consulted | People whose input is needed before the work can be done and signed off. Two-way communication.
I — Informed | People who need to be kept in the picture. One-way communication, no direct contribution.
R/A — Combination | The role both does the work and owns the result — typical for the BA on requirements and the Tech Lead on architecture and implementation.

## Instructions
Instructional Notes for the RACI Matrix
The RACI Matrix is a tool to assist in the identification of roles and the assigning of cross-functional responsibilities to a project deliverable or activity. It removes the situation where an activity is formally in the plan but no role treats it as their own.
RACI represents: R - Responsibility, A - Accountable, C - Consulted, and I - Informed.
Responsible: People or stakeholders who do the work. They must complete the task or objective or make the decision. Several people can be jointly Responsible.
Accountable: Person or stakeholder who is the owner of the work. He or she must sign off or approve when the task, objective or decision is complete, and must make sure that responsibilities are assigned for all related activities. Success requires that there is only one person Accountable.
Consulted: People or stakeholders who need to give input before the work can be done and signed off. These people are in the loop and are active participants.
Informed: People or stakeholders who need to be kept in the picture. They need updates on progress or decisions, but they are not formally consulted and do not contribute directly.
Rules applied in this matrix:
1. Every row has exactly one role marked Accountable (counting the R/A combination).
2. Every row has at least one Responsible role, otherwise nobody would perform the activity.
3. An empty cell means the role is not involved in that activity. This is a deliberate decision, not an omission.
4. The number of Consulted and Informed marks is kept moderate: too many C slows the work down, too many I turns communication into noise.
5. Only roles with high influence in the Stakeholder Register are ever Accountable. Low-influence roles (DevOps, QA, the Technical Department, end users) can be Responsible or Consulted, but never sign off.
6. Tech Lead, DevOps and QA are all software engineers (SWE), so all three are Responsible for implementing the product modules.
Relationship to the other artifacts:
- The roles in the columns correspond to the entries in “1. Stakeholder Register_VNS.xlsx”.
- Stakeholders marked Key Player in the register hold A or R in the key phases of this matrix.
- Stakeholders with low interest (the Ministry, the Project Manager, the Technical Department) are consulted only on decisions that concern them and are otherwise informed or not involved.
- The frequency and format of interaction for roles holding A, R or C are detailed in “4. Communication Plan_VNS.xlsx”.
Demonstration note: this is a training business case. The university stakeholders named here are addressed in a demonstration context and no real agreements have been concluded with them.