## SH Register
| Project Name | "VNS" — Custom University Learning Platform | Date | 02/10/2026
| Project Manager | Nazar Zankovych | Version | V1.2
| Project Sponsor | Lviv Polytechnic National University; Ministry of Education and Science of Ukraine | Project Start Date | 22/09/2026
| Project Phase | Initiation | Project End Date | 31/01/2027
|  |  | Author | Andrii Lysun (Business Analyst)
STAKEHOLDERS | Name | Category | Organization | Role/Job Title | Email | Phone | Communication Channel | Frequency | Location | Time Zone | Power* | Interest* | Approach* | Comments/Notes
| Full name of the stakeholder | Internal / External / Primary or Secondary | The name of the organization or group the stakeholder belongs to | Job title or role held by the stakeholder | Work Email and personal Email, with consent of individual | Primary + alternative contact info | Via email, Conference call, Message etc. | The frequency of communication to be done within a pre-defined timeframe | City and Country where the person is located | Time Zone which the person belongs to | High / Low | High / Low | Key Player / Keep Informed / Meet their needs etc. | Additional details to keep in mind
| Lviv Polytechnic National University | External / Primary | Lviv Polytechnic National University | Project Sponsor — customer and owner of the future platform | office@lpnu.ua | +380 (32) 258-21-11 | Meeting + written status report | Every two weeks, Tuesday | Lviv, Ukraine | EET (UTC+2) | High | High | Key Player | Funds the project, owns the current VNS platform and the student data, and represents the university leadership: approves the project charter and MVP scope and accepts the final result. Main interest is replacing the outdated Moodle-based platform and gaining engagement analytics.
| Ministry of Education and Science of Ukraine | External / Secondary | Ministry of Education and Science of Ukraine | Project Sponsor — sector regulator and funding source | office@mon.gov.ua | +380 (44) 481-32-21 | Official one-page report | Once per semester and at control points | Kyiv, Ukraine | EET (UTC+2) | High | Low | Meet their needs | Sets the regulatory framework for educational IT systems and for processing personal data in education, and can condition the scaling of the product beyond the pilot. Not involved in day-to-day work: kept satisfied through formal semester reporting and consulted only on decisions with regulatory impact.
| Technical Department of Lviv Polytechnic | External / Secondary | Lviv Polytechnic National University | Developers and administrators of the current VNS | it.support@lpnu.ua | +380 (32) 258-21-77 | E-mail / ticket on request | As needed (registry export, infrastructure access) | Lviv, Ukraine | EET (UTC+2) | Low | Low | Monitor | Built and maintain the current VNS. Because the project uses its own custom backend with no Moodle integration, the department neither controls delivery nor depends on its result. Involvement is limited to one-off requests: the export of the student registry and access to university infrastructure. Monitored in case they react to the replacement of their system.
| End users — students and lecturers | External / Primary | Students and teaching staff of Lviv Polytechnic National University | End users of the product: students and lecturers | Via learning channels and @lpnu.ua mailboxes | — | Interviews, surveys, usability tests, demos | Weekly during elicitation and the pilot | Lviv, Ukraine | EET (UTC+2) | Low | High | Keep Informed | Primary target audience in two roles. Students: scattered chats, misleading grade summary, empty calendar. Lecturers: course materials, assignments, activity analytics and the AI mode for graded work. No direct influence on decisions, but requirements not validated with them will be wrong.
| Kostiantyn Holovskyi | Internal / Primary | Project team “20/80” | Product Owner | kostiantyn.holovskyi.shi.2025@lpnu.ua | +380 (67) 000-00-01 | Team meeting + backlog | Weekly, Monday | Lviv, Ukraine | EET (UTC+2) | High | High | Key Player | Owns the product vision and backlog priorities. Approves the MVP scope and accepts the result from the product side.
| Nazar Zankovych | Internal / Primary | Project team “20/80” | Project Manager | nazar.zankovych.shi.2025@lpnu.ua | +380 (67) 000-00-02 | All project ceremonies | Daily | Lviv, Ukraine | EET (UTC+2) | High | Low | Meet their needs | High authority over the plan, schedule, resources and communications. Interest is in delivering on time and within scope rather than in the functional content of the product, which is owned by the Product Owner. Single point of contact for the sponsors.
| Andrii Lysun | Internal / Primary | Project team “20/80” | Business Analyst | andrii.lysun.shi.2025@lpnu.ua | +380 (67) 000-00-03 | Requirements elicitation meetings, workshops | Weekly + as needed | Lviv, Ukraine | EET (UTC+2) | High | High | Key Player | Elicits and documents requirements and produces the BA artifacts and UML models. Main contact for the end users — both students and lecturers.
| Denys Lunhul | Internal / Primary | Project team “20/80” | Tech Lead, Software Engineer (SWE) | denys.lunhul.shi.2025@lpnu.ua | +380 (67) 000-00-04 | Technical sync + code review | Weekly, Tuesday | Lviv, Ukraine | EET (UTC+2) | High | High | Key Player | Software engineer who also leads the technical side: owns the custom backend architecture, decides on the technology stack and is accountable for the technical feasibility of requirements.
| Yaroslav Shevchuk | Internal / Secondary | Project team “20/80” | DevOps, Software Engineer (SWE) | yaroslav.shevchuk.shi.2025@lpnu.ua | +380 (67) 000-00-05 | Daily stand-up + technical sync | Daily | Lviv, Ukraine | EET (UTC+2) | Low | Low | Monitor | Software engineer who also owns deployment, environments and CI/CD. Low influence: executes tasks agreed in planning and does not set scope or priorities. Low interest in the business outcome: engagement is at task level. Kept in the loop through the team's own ceremonies, so no separate stakeholder communication is needed.
| Volodymyr Kamelchuk | Internal / Secondary | Project team “20/80” | QA Specialist, Software Engineer (SWE) | volodymyr.kamelchuk.shi.2025@lpnu.ua | +380 (67) 000-00-06 | Daily stand-up + defect report | Daily | Lviv, Ukraine | EET (UTC+2) | Low | Low | Monitor | Software engineer who also verifies the acceptance criteria, in particular the grade forecast and the AI's refusal to produce complete solutions for graded work. Low influence and low interest in the business outcome; kept in the loop through the team's own ceremonies.
Legend
| Category | Internal — a member of the delivery team; External — a stakeholder on the university or state side. Primary — directly involved; Secondary — involved indirectly.
| Power* / Interest* | Power — the ability to affect scope, schedule and the decision to launch. Interest — how far the outcome affects the stakeholder's daily work or study. Values: High / Low.
| Approach* | High+High = Key Player (ENGAGE); High+Low = Meet their needs (SATISFY); Low+High = Keep Informed (INFORM); Low+Low = Monitor (MONITOR).
| Contact details | Phone numbers are illustrative placeholders for this training project. Team e-mail addresses follow the real Lviv Polytechnic National University format.

## RACI
Legend: | R | Responsible
| A | Accountable
| C | Consulted
| I | Informed
Phase | Role | Lviv Polytechnic National University (Project Sponsor) | Ministry of Education and Science (Sponsor, regulator) | Product Owner (K. Holovskyi) | Project Manager (N. Zankovych) | Business Analyst (A. Lysun) | Tech Lead / SWE (D. Lunhul) | DevOps / SWE (Y. Shevchuk) | QA / SWE (V. Kamelchuk) | Technical Department of Lviv Polytechnic | End users — students and lecturers
Activity
Initiation | Agree on the problem statement and business context (audit of the current VNS) | A |  | R | R | R | C | I | I | I | C
| Identify and analyse stakeholders (register, power/interest matrix) | C |  | C | A | R | I | I | I |  | I
| Approve the strategy: custom backend instead of Moodle integration | A |  | R | C | C | R | C | I | I | I
| Develop the business case and the success metrics | C | C | A | R | R | C | I | I |  | I
| Approve the project charter and the MVP scope | A | C | R | R | C | C | I | I |  | I
Planning | Elicit and document requirements (interviews with lecturers, student surveys) | I |  | C | I | R/A | C | I | C |  | C
| Build UML models (use case, activity) for the product scenarios |  |  | C | I | R/A | C | I | C |  | I
| Design the data model and the custom backend architecture |  |  | C | I | C | R/A | R | C
| Approve processing of student personal data and transfer of materials to the LLM API | A | C | C | R | R | C | I | I | I | I
| Produce the communications plan and the project schedule | C |  | C | R/A | R | C | I | I
| Select the technology stack and the LLM API provider | C |  | C | C | I | A | R | C
Execution | Obtain the student registry; implement registration and authentication | C |  | C | I | C | R/A | R | R | R | I
| Implement courses, materials, deadlines and grade forecasting |  |  | C | I | C | R/A | R | R |  | C
| Implement the communication hub and Study Spaces |  |  | C | I | C | R/A | R | R |  | C
| Implement the AI assistant: summaries, quizzes, “Ask the course” | I |  | A | I | C | R | R | R |  | C
| Set up environments and configure CI/CD |  |  | I | I |  | A | R | C | C
| Run testing and acceptance checks |  |  | A | I | C | C | C | R |  | C
| Deploy the platform to the production environment | I |  | I | C | I | A | R | C | C | I
Control | Manage scope changes and backlog priorities | C |  | A | R | R | C | I | I |  | I
| Control quality, defects and adherence to the acceptance criteria |  |  | C | I | C | A | I | R |  | C
| Monitor LLM API costs, quotas and request limits | C |  | I: C; C: R/A; A: C; R: R
| Report project status to the sponsors | I | I | I: C; C: R/A; I: R; A: C
Close | Run the pilot with students and lecturers and collect feedback | C |  | A | R | R | C | C | C |  | R
| Hand over the system and documentation to the sponsor | C |  | R | A | R | R | R | C | I
| Capture lessons learned and close the project | I |  | C | A | R | C | C | C

## SH Matrix
low POWER high |  | SATISFY |  |  |  |  | ENGAGE
| Ministry of Education and Science (Sponsor) |  | Project Manager N. Zankovych |  | Lviv Polytechnic National University (Sponsor) | Product Owner K. Holovskyi |  | Business Analyst A. Lysun
Tech Lead / SWE D. Lunhul
|  | MONITOR |  |  |  |  | INFORM
| Technical Department of Lviv Polytechnic |  | DevOps / SWE Y. Shevchuk | QA / SWE V. Kamelchuk | End users — students and lecturers
low INTEREST high