## Communication_Plan
Communication Plan – "VNS" – Custom University Learning Platform
Communication | Method | Frequency | Goal | Owner | Audience
Team Standup | Meeting (online) | Daily, 10:00, 15 min | Synchronise progress since the previous day, raise blockers and redistribute work within the team | Project Manager (N. Zankovych) | Whole project team: PO, PM, BA, Tech Lead, DevOps, QA
Weekly Planning and Backlog Review | Meeting | Weekly, Monday | Agree the scope of work for the week and the MVP backlog priorities; confirm the definition of ready | Product Owner (K. Holovskyi) | PO, PM, BA, Tech Lead, DevOps, QA
Requirements Elicitation Meeting with Lecturers | Interview / workshop | Weekly, Thursday | Clarify lecturer scenarios: materials, assignments, activity analytics, AI mode for graded work | Business Analyst (A. Lysun) | End users — lecturers, BA; PO and Tech Lead as needed
End-user Feedback Session | Survey + usability test | Weekly during the pilot | Validate prototypes with students and lecturers and collect pain points on deadlines, grade forecast and communication | Business Analyst (A. Lysun) | End users — students and lecturers, BA, QA, PO
Technical Sync | Meeting + code review | Weekly, Tuesday | Discuss the custom backend architecture, the data model, deployment, technical debt and dependencies between modules | Tech Lead (D. Lunhul) | Software engineers (Tech Lead, DevOps, QA), PM; BA as needed
Quality and Defect Report | Written report + dashboard | Weekly, Friday | Report the state of the acceptance criteria, open defects and release risks, including grade forecast correctness | QA Specialist (V. Kamelchuk) | QA, PM, PO, Tech Lead
Requests to the University Technical Department | E-mail / ticket | As needed (registry export, infrastructure access) | Request the export of the student registry and access to university infrastructure, domain and certificates | DevOps (Y. Shevchuk) | Technical Department of Lviv Polytechnic, DevOps, Tech Lead
Status Report to the Sponsor | Meeting + written report | Every two weeks, Tuesday | Present progress, risks and decisions requiring escalation; confirm the scope for the next period | Project Manager (N. Zankovych) | Lviv Polytechnic National University, PM, PO, BA
Increment Demo for the Sponsor and End Users | Demo + working meeting | Monthly | Show the working increment, confirm that it matches the requirements and collect corrections | Product Owner (K. Holovskyi) | Lviv Polytechnic National University, end-user representatives, PO, PM, BA, QA
Team Retrospective | Meeting | Every two weeks, Friday | Identify what works and what does not, and agree concrete process improvements for the next two weeks | Project Manager (N. Zankovych) | Whole project team
Change Management Meeting | Meeting | As needed, within 2 business days of a request | Review a scope change request, assess the impact on the schedule and take a decision | Product Owner (K. Holovskyi) | PO, PM, BA, Tech Lead; the sponsor for material changes
Semester Report to the Ministry of Education and Science | Official one-page report | Once per semester and at control points | Keep the regulator satisfied: report progress, pilot results and compliance with personal-data and educational IT regulation | Project Manager (N. Zankovych) | Ministry of Education and Science of Ukraine, Lviv Polytechnic National University, PM