## Stakeholder register
Stakeholder Register
Project Name | "VNS" — Custom University Learning Platform |  |  |  |  | Date | 23/09/2026
Project Manager | Nazar Zankovych (nazar.zankovych.shi.2025@lpnu.ua) |  |  |  |  | Version | V1.1
Project Sponsor | Lviv Polytechnic National University; Ministry of Education and Science of Ukraine |  |  |  |  | Project Start Date | 22/09/2026
Project Phase | Initiation |  |  |  |  | Project End Date | 31/01/2027
Author | Andrii Lysun (Business Analyst) |  |  |  |  | Status | Draft for team approval
Stakeholder Name | Category | Stakeholder Group | Organization or Group | Role or Job title | Power/Influence | Interest | Address | Phone number | Email address | Preferable way of communication | Frequency of Communication | Comments and notes
Full name of the stakeholder | Internal / External / Primary or Secondary | Key Player / Keep Informed / Meet their needs etc | The name of the organization or group the stakeholder belongs to | Job title or role held by the stakeholder | High / Low | High / Low | Primary contact address | Primary + alternative contact info | Work Email and personal Email, with consent of individual | If phone, meetings or email | Record of letters, phone calls sent to stakeholder | Known contacts affiliations etc.
Lviv Polytechnic National University | External / Primary | Key Player | Lviv Polytechnic National University | Project Sponsor — customer and owner of the future platform | High | High | 12 S. Bandery Street, Lviv, 79013, Ukraine | +380 (32) 258-21-11 | office@lpnu.ua | Meeting + written status report | Every two weeks, Tuesday | Funds the project and owns the current VNS platform and the student data. Approves scope and accepts the final result. Main interest is replacing the outdated Moodle-based platform and gaining engagement analytics.
Ministry of Education and Science of Ukraine | External / Secondary | Meet their needs | Ministry of Education and Science of Ukraine | Project Sponsor — sector regulator and funding source | High | Low | 10 Peremohy Avenue, Kyiv, 01135, Ukraine | +380 (44) 481-32-21 | office@mon.gov.ua | Official report | Once per semester | Not involved in day-to-day work, but defines the regulatory requirements for educational IT systems and sector funding. Communication is formal reporting at control points only.
Nataliia Shakhovska | External / Primary | Meet their needs | Rector's Office, Lviv Polytechnic National University | Rector of Lviv Polytechnic National University | High | Low | 12 S. Bandery Street, Lviv, 79013, Ukraine | +380 (32) 258-26-00 | nataliia.b.shakhovska@lpnu.ua | E-mail with a one-page summary | Once per semester and at control points | Highest decision-making authority in the university: approves the project charter and is the person who can authorise scaling the product beyond the pilot. Not involved day to day — summary communication only.
Nataliia Boiko | External / Primary | Key Player | Lviv Polytechnic National University | Lecturer — customer and end user | High | High | 12 S. Bandery Street, Lviv, 79013, Ukraine | +380 (32) 258-25-30 | nataliia.i.boiko@lpnu.ua | Interview, requirements workshop, increment demo | Weekly, Thursday | Dual role: defines and accepts requirements while also being a future user of the product. Key source of lecturer-facing requirements — course materials, assignments, activity analytics, and the AI mode for graded work.
Technical Department of Lviv Polytechnic | External / Primary | Key Player | Lviv Polytechnic National University | Developers and administrators of the current VNS | High | High | 12 S. Bandery Street, Lviv, 79013, Ukraine | +380 (32) 258-21-77 | it.support@lpnu.ua | Working meeting + e-mail | Every two weeks | Own the current VNS, the infrastructure and the student registry, without which registration cannot work. Risk of resistance: the project replaces the system they built — engage them as partners rather than as a supplier.
End users — Lviv Polytechnic students | External / Primary | Keep Informed | Student body of Lviv Polytechnic National University | End users of the product | Low | High | 12 S. Bandery Street, Lviv, 79013, Ukraine | — | Via learning channels and @lpnu.ua mailboxes | Survey, usability test, announcement | Weekly during the pilot | Primary target audience. Source of evidence on the real pain points: scattered chats, misleading grade summary, empty calendar. No direct influence on decisions, but requirements not validated with them will be wrong.
Kostiantyn Holovskyi | Internal / Primary | Key Player | Project team “VNS”, group SHI-2025 | Product Owner | High | High | 12 S. Bandery Street, Lviv, 79013, Ukraine | +380 (67) 000-00-01 | kostiantyn.holovskyi.shi.2025@lpnu.ua | Team meeting + backlog | Weekly, Monday | Owns the product vision and backlog priorities. Approves the MVP scope and accepts the result from the product side.
Nazar Zankovych | Internal / Primary | Key Player | Project team “VNS”, group SHI-2025 | Project Manager | High | High | 12 S. Bandery Street, Lviv, 79013, Ukraine | +380 (67) 000-00-02 | nazar.zankovych.shi.2025@lpnu.ua | All project ceremonies | Daily | Responsible for the plan, schedule and communications. Single point of contact for the sponsors, the Rector's office and the Technical Department.
Andrii Lysun | Internal / Primary | Key Player | Project team “VNS”, group SHI-2025 | Business Analyst | High | High | 12 S. Bandery Street, Lviv, 79013, Ukraine | +380 (67) 000-00-03 | andrii.lysun.shi.2025@lpnu.ua | Requirements elicitation meetings, workshops | Weekly + as needed | Elicits and documents requirements and produces the BA artifacts and UML models. Main contact for Nataliia Boiko and the end users.
Denys Lunhul | Internal / Primary | Key Player | Project team “VNS”, group SHI-2025 | Tech Lead | High | High | 12 S. Bandery Street, Lviv, 79013, Ukraine | +380 (67) 000-00-04 | denys.lunhul.shi.2025@lpnu.ua | Technical sync + code review | Weekly, Tuesday | Responsible for the custom backend architecture and the technical feasibility of requirements. Decides on the technology stack.
Yaroslav Shevchuk | Internal / Secondary | Keep Informed | Project team “VNS”, group SHI-2025 | DevOps | Low | High | 12 S. Bandery Street, Lviv, 79013, Ukraine | +380 (67) 000-00-05 | yaroslav.shevchuk.shi.2025@lpnu.ua | Daily stand-up + technical sync | Daily | Deployment, environments, CI/CD, queue and workers for AI tasks. Main contact with the university Technical Department.
Volodymyr Kamelchuk | Internal / Secondary | Keep Informed | Project team “VNS”, group SHI-2025 | QA Specialist | Low | High | 12 S. Bandery Street, Lviv, 79013, Ukraine | +380 (67) 000-00-06 | volodymyr.kamelchuk.shi.2025@lpnu.ua | Daily stand-up + defect report | Daily | Verifies the acceptance criteria, in particular the correctness of the grade forecast and the AI's refusal to produce complete solutions for graded work.
LEGEND AND COMPLETION RULES
Category | Internal — a member of the delivery team; External — a stakeholder on the university or state side. Primary — directly involved; Secondary — involved indirectly.
Stakeholder Group | Derived from Power/Influence × Interest: High+High = Key Player (ENGAGE); High+Low = Meet their needs (SATISFY); Low+High = Keep Informed (INFORM); Low+Low = Monitor (MONITOR).
MONITOR quadrant | The approved stakeholder list contains nobody with both low influence and low interest, so the MONITOR quadrant is deliberately left empty.
Contact details | Phone numbers are illustrative placeholders for this training project. Team e-mail addresses follow the real Lviv Polytechnic National University format.