## Communication_Plan
Communication Plan — "VNS" — Custom University Learning Platform
Project Phase | Initiation |  | Date | 23/09/2026
Plan Owner | Nazar Zankovych, Project Manager |  | Version | V1.1
Working language | English for documentation; Ukrainian for day-to-day team work |  | Validity period | 22/09/2026 – 31/01/2027
Communication | Method | Frequency | Goal | Owner | Audience
Team Standup | Meeting (online) | Daily, 10:00, 15 min | Synchronise progress since the previous day, raise blockers and redistribute work within the team | Project Manager (N. Zankovych) | Whole project team: PO, PM, BA, Tech Lead, DevOps, QA
Weekly Planning and Backlog Review | Meeting | Weekly, Monday | Agree the scope of work for the week and the MVP backlog priorities; confirm the definition of ready | Product Owner (K. Holovskyi) | PO, PM, BA, Tech Lead, DevOps, QA
Requirements Elicitation Meeting with the Customer | Interview / workshop | Weekly, Thursday | Clarify lecturer scenarios: materials, assignments, activity analytics, AI mode for graded work | Business Analyst (A. Lysun) | Nataliia Boiko, BA; PO and Tech Lead as needed
End-user Feedback Session | Survey + usability test | Weekly during the pilot | Validate prototypes with real students and collect pain points on deadlines, grade forecast and communication | Business Analyst (A. Lysun) | End users — Lviv Polytechnic students, BA, QA, PO
Technical Sync | Meeting + code review | Weekly, Tuesday | Discuss the custom backend architecture, the data model, technical debt and dependencies between modules | Tech Lead (D. Lunhul) | Tech Lead, DevOps, QA, PM; BA as needed
Quality and Defect Report | Written report + dashboard | Weekly, Friday | Report the state of the acceptance criteria, open defects and release risks, including grade forecast correctness | QA Specialist (V. Kamelchuk) | QA, PM, PO, Tech Lead
Coordination with the University Technical Department | Working meeting + e-mail | Every two weeks | Agree access to the student registry, infrastructure, domain, certificates and the security policy | DevOps (Y. Shevchuk) | Technical Department of Lviv Polytechnic, DevOps, Tech Lead, PM
Status Report to the Sponsor | Meeting + written report | Every two weeks, Tuesday | Present progress, risks and decisions requiring escalation; confirm the scope for the next period | Project Manager (N. Zankovych) | Lviv Polytechnic National University, Nataliia Boiko, PM, PO, BA
Team Retrospective | Meeting | Every two weeks, Friday | Identify what works and what does not, and agree concrete process improvements for the next two weeks | Project Manager (N. Zankovych) | Whole project team
Increment Demo for the Customer | Demo + working meeting | Monthly | Show the working increment, confirm that it matches the requirements and collect corrections | Product Owner (K. Holovskyi) | Nataliia Boiko, PO, PM, BA, QA
Summary for the Rector's Office | E-mail with a one-page summary | Once per semester and at control points | Report status, pilot results and the decision needed on scaling the product across the university | Project Manager (N. Zankovych) | Nataliia Shakhovska (Rector), Lviv Polytechnic National University, PM
Reporting to the Ministry of Education and Science | Official report | Once per semester | Inform the regulator about the course and results of the project and its compliance with regulatory requirements | Project Manager (N. Zankovych) | Ministry of Education and Science of Ukraine, Lviv Polytechnic National University, Rector, PM
LLM API Cost and Quota Review | E-mail + support ticket | Monthly and on tariff changes | Control the cost of the AI module, the daily request limits per user and the data processing terms | Project Manager (N. Zankovych) | PM, Tech Lead, DevOps, Lviv Polytechnic National University
Change Management Meeting | Meeting | As needed, within 2 business days of a request | Review a scope change request, assess the impact on the schedule and take a decision | Product Owner (K. Holovskyi) | PO, PM, BA, Tech Lead; Nataliia Boiko for material changes
Pilot Announcement to End Users | Announcement in learning channels | Before the pilot and monthly thereafter | Recruit pilot participants, explain the value of the product and collect sign-ups | Product Owner (K. Holovskyi) | End users — Lviv Polytechnic students, PO, PM
Project Handover and Closure | Meeting + documentation package | Once, at the end of the project | Hand over the system, documentation and lessons learned to the customer and sign the acceptance record | Project Manager (N. Zankovych) | Lviv Polytechnic National University, Nataliia Boiko, Technical Department, whole team
COMMUNICATION ESCALATION PROCESS
Priority | Definition |  | Decision Authority | Timeframe for Resolution
Priority 1 | Major impact: the team is blocked, or the pilot or project deadline is at risk |  | Lviv Polytechnic National University (Sponsor) | Within 1 business day
Priority 2 | Medium impact: individual activities or the MVP scope may slip |  | Product Owner | Within 2 business days
Priority 3 | Slight impact: minor scheduling difficulties with no effect on scope or outcome |  | Project Manager | Within 3 business days
Priority 4 | No impact on the project, but a better solution may exist |  | Project Manager | Handled through the change management process
COMMUNICATION STANDARDS
Meeting agenda | Distributed to participants no later than 2 business days before the meeting; identifies the topics, the presenter and a time limit for each. The first item is always a review of action items from the previous meeting.
Meeting minutes | Published within 1 business day after the meeting; contain the decisions taken, new action items with a named owner and due date, and the Parking Lot list.
Channels | Formal documents and approvals — university @lpnu.ua mailboxes. Day-to-day team work — team chat. Tasks and defects — issue tracker.
Confidentiality | Personal data of students and lecturers is not distributed through external channels. Any transfer of course materials to the external LLM API is approved by Lviv Polytechnic National University as the owner of the data.
Escalation rule | Issues involving personal data or the transfer of materials to the external LLM API are escalated to the sponsor regardless of the priority assigned.
Link to the register | The frequency and method of each communication match the “Preferable way of communication” and “Frequency of Communication” columns in “1. Stakeholder Register_VNS.xlsx”.