## SH Register
| Project Name | "VNS" — Custom University Learning Platform | Date | 23/09/2026
| Project Manager | Nazar Zankovych | Version | V1.1
| Project Sponsor | Lviv Polytechnic National University; Ministry of Education and Science of Ukraine | Project Start Date | 22/09/2026
| Project Phase | Initiation | Project End Date | 31/01/2027
|  |  | Author | Andrii Lysun (Business Analyst)
STAKEHOLDERS | Name | Category | Organization | Role/Job Title | Email | Phone | Communication Channel | Frequency | Location | Time Zone | Power* | Interest* | Approach* | Comments/Notes
| Full name of the stakeholder | Internal / External / Primary or Secondary | The name of the organization or group the stakeholder belongs to | Job title or role held by the stakeholder | Work Email and personal Email, with consent of individual | Primary + alternative contact info | Via email, Conference call, Message etc. | The frequency of communication to be done within a pre-defined timeframe | City and Country where the person is located | Time Zone which the person belongs to | High / Low | High / Low | Key Player / Keep Informed / Meet their needs etc. | Additional details to keep in mind
| Lviv Polytechnic National University | External / Primary | Lviv Polytechnic National University | Project Sponsor — customer and owner of the future platform | office@lpnu.ua | +380 (32) 258-21-11 | Meeting + written status report | Every two weeks, Tuesday | Lviv, Ukraine | EET (UTC+2) | High | High | Key Player | Funds the project and owns the current VNS platform and the student data. Approves scope and accepts the final result. Main interest is replacing the outdated Moodle-based platform and gaining engagement analytics.
| Ministry of Education and Science of Ukraine | External / Secondary | Ministry of Education and Science of Ukraine | Project Sponsor — sector regulator and funding source | office@mon.gov.ua | +380 (44) 481-32-21 | Monitoring of national regulation | Ad hoc, if regulation changes | Kyiv, Ukraine | EET (UTC+2) | Low | Low | Monitor | Formal sponsor of the sector, but for a pilot inside a single department the ministry has neither influence over delivery nor day-to-day interest in it. Monitored only in case the national regulation of educational IT systems changes; no recurring communication and no project activity is assigned to it.
| Nataliia Shakhovska | External / Primary | Rector's Office, Lviv Polytechnic National University | Rector of Lviv Polytechnic National University | nataliia.b.shakhovska@lpnu.ua | +380 (32) 258-26-00 | E-mail with a one-page summary | Once per semester and at control points | Lviv, Ukraine | EET (UTC+2) | High | Low | Meet their needs | Highest decision-making authority in the university: approves the project charter and is the person who can authorise scaling the product beyond the pilot. Not involved day to day — summary communication only.
| Nataliia Boiko | External / Primary | Lviv Polytechnic National University | Lecturer — customer and end user | nataliia.i.boiko@lpnu.ua | +380 (32) 258-25-30 | Interview, requirements workshop, increment demo | Weekly, Thursday | Lviv, Ukraine | EET (UTC+2) | High | High | Key Player | Dual role: defines and accepts requirements while also being a future user of the product. Key source of lecturer-facing requirements — course materials, assignments, activity analytics, and the AI mode for graded work.
| Technical Department of Lviv Polytechnic | External / Primary | Lviv Polytechnic National University | Developers and administrators of the current VNS | it.support@lpnu.ua | +380 (32) 258-21-77 | Working meeting + e-mail | Every two weeks | Lviv, Ukraine | EET (UTC+2) | High | High | Key Player | Own the current VNS, the infrastructure and the student registry, without which registration cannot work. Risk of resistance: the project replaces the system they built — engage them as partners rather than as a supplier.
| End users — Lviv Polytechnic students | External / Primary | Student body of Lviv Polytechnic National University | End users of the product | Via learning channels and @lpnu.ua mailboxes | — | Survey, usability test, announcement | Weekly during the pilot | Lviv, Ukraine | EET (UTC+2) | Low | High | Keep Informed | Primary target audience. Source of evidence on the real pain points: scattered chats, misleading grade summary, empty calendar. No direct influence on decisions, but requirements not validated with them will be wrong.
| Kostiantyn Holovskyi | Internal / Primary | Project team “20/80” | Product Owner | kostiantyn.holovskyi.shi.2025@lpnu.ua | +380 (67) 000-00-01 | Team meeting + backlog | Weekly, Monday | Lviv, Ukraine | EET (UTC+2) | High | High | Key Player | Owns the product vision and backlog priorities. Approves the MVP scope and accepts the result from the product side.
| Nazar Zankovych | Internal / Primary | Project team “20/80” | Project Manager | nazar.zankovych.shi.2025@lpnu.ua | +380 (67) 000-00-02 | All project ceremonies | Daily | Lviv, Ukraine | EET (UTC+2) | High | High | Key Player | Responsible for the plan, schedule and communications. Single point of contact for the sponsors, the Rector's office and the Technical Department.
| Andrii Lysun | Internal / Primary | Project team “20/80” | Business Analyst | andrii.lysun.shi.2025@lpnu.ua | +380 (67) 000-00-03 | Requirements elicitation meetings, workshops | Weekly + as needed | Lviv, Ukraine | EET (UTC+2) | High | High | Key Player | Elicits and documents requirements and produces the BA artifacts and UML models. Main contact for Nataliia Boiko and the end users.
| Denys Lunhul | Internal / Primary | Project team “20/80” | Tech Lead | denys.lunhul.shi.2025@lpnu.ua | +380 (67) 000-00-04 | Technical sync + code review | Weekly, Tuesday | Lviv, Ukraine | EET (UTC+2) | High | High | Key Player | Responsible for the custom backend architecture and the technical feasibility of requirements. Decides on the technology stack.
| Yaroslav Shevchuk | Internal / Secondary | Project team “20/80” | DevOps | yaroslav.shevchuk.shi.2025@lpnu.ua | +380 (67) 000-00-05 | Daily stand-up + technical sync | Daily | Lviv, Ukraine | EET (UTC+2) | Low | High | Keep Informed | Deployment, environments, CI/CD, queue and workers for AI tasks. Main contact with the university Technical Department.
| Volodymyr Kamelchuk | Internal / Secondary | Project team “20/80” | QA Specialist | volodymyr.kamelchuk.shi.2025@lpnu.ua | +380 (67) 000-00-06 | Daily stand-up + defect report | Daily | Lviv, Ukraine | EET (UTC+2) | Low | High | Keep Informed | Verifies the acceptance criteria, in particular the correctness of the grade forecast and the AI's refusal to produce complete solutions for graded work.
Legend
| Category | Internal — a member of the delivery team; External — a stakeholder on the university or state side. Primary — directly involved; Secondary — involved indirectly.
| Power* / Interest* | Power — the ability to affect scope, schedule and the decision to launch. Interest — how far the outcome affects the stakeholder's daily work or study. Values: High / Low.
| Approach* | High+High = Key Player (ENGAGE); High+Low = Meet their needs (SATISFY); Low+High = Keep Informed (INFORM); Low+Low = Monitor (MONITOR).
| Contact details | Phone numbers are illustrative placeholders for this training project. Team e-mail addresses follow the real Lviv Polytechnic National University format.

## RACI
Legend: | R | Responsible
| A | Accountable
| C | Consulted
| I | Informed
Phase | Role | Lviv Polytechnic National University (Project Sponsor) | Nataliia Shakhovska (Executive Sponsor, Rector) | Product Owner (K. Holovskyi) | Project Manager (N. Zankovych) | Business Analyst (A. Lysun) | Tech Lead (D. Lunhul) | DevOps (Y. Shevchuk) | QA Specialist (V. Kamelchuk) | Nataliia Boiko (Customer / End user) | Technical Department of Lviv Polytechnic | End users — students
Activity
Initiation | Agree on the problem statement and business context (audit of the current VNS) | A | I | R | R | R | C | I | I | C | C | C
| Identify and analyse stakeholders (register, power/interest matrix) | C | I | C | A | R | I | I | I | C | I | I
| Approve the strategy: custom backend instead of Moodle integration | A | I | R | C | C | R | C | I | C | C | I
| Develop the business case and the success metrics | C | I | A | R | R | C | I | I | C | I | I
| Approve the project charter and the MVP scope | C | A | R | R | C | C | I | I | C | I | I
Planning | Elicit and document requirements (customer interviews, end-user surveys) | I |  | C | C | R/A | C | I | C | C | C | C
| Build UML models (use case, activity) for the product scenarios | I |  | C | C | R/A | C | I | C | C | I | I
| Design the data model and the custom backend architecture | I |  | C | C | C | R/A | R | C | I | C
| Approve processing of student personal data and transfer of materials to the LLM API | A | C | C | R | R | C | C | I | C | C | I
| Produce the communications plan and the project schedule | C | I | C | R/A | R | C | C | C | C | I | I
| Select the technology stack and the LLM API provider | C | I | C | C | C | A | R | C | I | C
Execution | Obtain the student registry; implement registration and authentication | C |  | C | C | C | A | R | C | I | R | I
| Implement courses, materials, deadlines and grade forecasting | I |  | C | I | C | R/A | I | C | C | I | I
| Implement the communication hub and Study Spaces | I |  | C | I | C | R/A | R | C | C | I | C
| Implement the AI assistant: summaries, quizzes, “Ask the course” | I |  | A | I | C | R | R | C | C | I | C
| Set up environments and configure CI/CD | I |  | I | I | I | C | R/A | C |  | C
| Run testing and acceptance checks | I |  | C | C | C | C | C | R/A | C | I | C
Control | Manage scope changes and backlog priorities | C | I | A | R | R | C | I | I | C | I | I
| Control quality, defects and adherence to the acceptance criteria | I |  | C | C | C | C | I | R/A | C | I | C
| Monitor LLM API costs, quotas and request limits | C | I | C | R/A | I | C | R |  |  | I
| Report project status to the sponsors and the Rector's office | I | I | C | R/A | R | C | I | C | I | I | I
Close | Run the pilot with students and collect feedback | C | I | A | R | R | C | C | C | R | C | R
| Hand over the system and documentation to the Technical Department and the customer | C | C | R | A | R | R | R | C | C | R | I
| Capture lessons learned and close the project | C | I | C | A | R | C | C | C | C | C | I

## SH Matrix
low POWER high |  | SATISFY |  |  | ENGAGE
| Nataliia Shakhovska Rector |  | Lviv Polytechnic National University (Sponsor) | Nataliia Boiko Customer & End user |  | Technical Department of Lviv Polytechnic
|  |  | Product Owner K. Holovskyi | Project Manager N. Zankovych |  | Business Analyst A. Lysun
Tech Lead D. Lunhul
|  | MONITOR |  |  | INFORM
| Ministry of Education and Science (Sponsor) |  | End users — students | DevOps Y. Shevchuk |  | QA Specialist V. Kamelchuk
low INTEREST high