## RACI Matrix
RACI Matrix Template
| Project Leadership |  |  |  | Project Team Members |  |  |  | Project Sub-Teams |  |  |  | External Resources
| Executive Sponsor | Project Sponsor | Product Owner | Product Manager | Project Manager | Delivery Manager | Solution Architect | Functional Lead (Scrum Master) | Developer | DevOps | Business Analyst | Quality Assurance | SME | Integration Coordinator
Initiation Phase
- Submit Project Request | A | R | C | C | R | I/R | C | C |  |  |  |  | C | C/I
- Request Review by PMO |  |  | A | A | R | I | I | [6 empty] | C/I
- Research Solution | I | C | C | R | R | I | A | I |  |  | C |  | C | C
- Develop Business Case | I | C/I | C | A | R |  | C | C |  |  | C |  | C | C
Planing Phase
- Create Project Charter | C | C | C | R | A | C | C | C |  |  | C | I | C | C
- Create Schedule | I | I | I | I | A | R | C | C | C | C | C | I | C | I
- Create Additional Plans as required | I | I | I | I | R | A |  |  | I | I | I | C |  | I
Execution Phase
- Build Deliverables | C/I | C/I | I | I | C/I | I | R | R | A | I | C/I | I | R/A | C
- Create Status Report | I | I | I | I | R | A | R | R |  |  | C | C | C | I
Control Phase
- Perform Change Management |  | C | I | I | R | I | C | C | C | C | A | I | C | I
Close Phase
- Create Lessons Learned | C | C | C | C | A | R | C | C | C | C | C | C | C | C
- Create Project Closure Report | I | I | I | I | A | R | I | I | I | I | I | I | I | I
Role
Project Deliverable
(or Activity)

## Instructions
Instructional Notes for the RACI Matrix:
The RACI Matrix is a powerful tool to assist in the identification of roles and assigning of cross-functional responsibilities to a project deliverable or activity. RACI represents: R - Responsibility, A - Accountable, C - Consulted, and I - Informed RACI Definitions: Responsible: People or stakeholders who do the work. They must complete the task or objective or make the decision. Several people can be jointly Responsible. Accountable: Person or stakeholder who is the “owner” of the work. He or she must sign off or approve when the task, objective or decision is complete. This person must make sure that responsibilities are assigned in the matrix for all related activities. Success requires that there is only one person Accountable, which means that “the buck stops there.” Consulted: People or stakeholders who need to give input before the work can be done and signed-off on. These people are “in the loop” and active participants. Informed: People or stakeholders who need to be kept “in the picture.” They need updates on progress or decisions, but they do not need to be formally consulted, nor do they contribute directly to the task or decision.