## Stakeholder register
Stakeholder Register
Project Name | “CoZy” home-office |  |  |  |  | Date | 20/07/2022
Project Manager | William Frederickson (William.Frederickson@cozy_home.com) |  |  |  |  | Version | V1
Project Sponsor | Konrad Cozeman |  |  |  |  | Project Start Date | 20/01/2023
Project Phase | Initiation |  |  |  |  | Project End Date | 15/11/2026
Stakeholder Name | Category | Stakeholder Group | Organization or Group | Role or Job title | Power/Influence | Interest | Address | Phone number | Email address | Preferable way of communication | Frequency of Communication | Comments and notes
Full name of the stakeholder | Internal / External / Primary or Secondary | Key Player / Keep Informed / Meet their needs etc | The name of the organization or group the stakeholder belongs to | Job title or role held by the stakeholder | High / Low | High / Low | Primary contact address | Primary + alternative contact info | Work Email and personal Email, with consent of individual | If phone, meetings or email | Record of letters, phone calls sent to stakeholder | Known contacts affiliations etc.
Ben Kordan | External/Primary | Key Player/Meet requirements | “CoZy” home-office | Product owner/Product manager | High | High | 5454 Interstate 55 North Frontage Rd, Jackson, MS 39211, United States | 18143008346 | William.Frederickson@cozy_home.com | Regular meeting/every Monday | regular report after meeting
Greg Larson | External/Primary | Key Player/Meet requirements | “CoZy” home-office | Project Manager | High | High | 5454 Interstate 55 North Frontage Rd, Jackson, MS 39211, United States | 18143008347 | Greg.Larson@cozy_home.com | Bi-weekly meeting/every Tuesday | regular report after meeting
Fran Olsen | External/Secondary | Keep Informed | “CoZy” home-office | Solution Architect | High | High | 5454 Interstate 55 North Frontage Rd, Jackson, MS 39211, United States | 18143008348 | Fran.Olsen@cozy_home.com | Meeting upon necessity | summary email
Mary Crowly | Internal/ Primary | Keep Informed | EPAM | Delivery Manager | High | High | M. Hrushevskoho str., 12/2. Kyiv, Ukraine, 01008 | +380956852463 | Mary.Crowly@epam.com | Meeting every Wednesday | reporting and summary of done work
Rory Lebowski | Internal/ Secondary | Keep Informed | EPAM | Scrum Master | Low | High | M. Hrushevskoho str., 12/2. Kyiv, Ukraine, 01008 | +380956852445 | Rory.Lebowski@epam.com | Daily scrum meetings | every day stand up
Sam Forting | Internal | Keep Informed | EPAM | Developer | Low | High | M. Hrushevskoho str., 12/2. Kyiv, Ukraine, 01008 | +380956852445 | Sam.Forting@epam.com | Daily scrum meetings | every day stand up
Beth Wendly | Internal | Keep Informed | EPAM | DevOps | Low | High | M. Hrushevskoho str., 12/2. Kyiv, Ukraine, 01008 | +380956852445 | Beth.Wendly@epam.com | Daily scrum meetings | every day stand up
Lan Browdy | Internal | Keep Informed | EPAM | QA Specialist | Low | High | M. Hrushevskoho str., 12/2. Kyiv, Ukraine, 01008 | +380956852445 | Lan.Browdy@epam.com | Daily scrum meetings | every day stand up
Otto Yukuhira | Internal/ Secondary | Keep Informed | Agiliway | SME | High | Low | 5454 Interstate 55 North Frontage Rd, Jackson, MS 39211, United States | 18143008348 | Otto.Yukuhira@cozy_home.com | Meeting every Wednesday | summary email
Peter Nilsen | Internal/ Secondary | Keep Informed | Agiliway | Integration coordinator | Low | Low | 5454 Interstate 55 North Frontage Rd, Jackson, MS 39211, United States | 18143008348 | Peter.Nilsen@cozy_home.com | Meeting every Wednesday | summary email