## Action Items (hidden)
[5 empty] | Engagement Manager: | Tiffany Jansen
Last Update:
|  |  | High | Medium | Low | Total | % Of Total
|  | Complete | 0 | 0 | 0 | 0 | 0%
|  | In Progress | 0 | 0 | 0 | 0 | 0%
|  | Behind | 0 | 0 | 0 | 0 | 0%
|  | Not Started | 0 | 0 | 0 | 0 | 0%
|  | Total | 0 | 0 | 0 | 0
|  | % Of Total | 0% | 0% | 0%
ID | Description | Comments | Status | Priority | Due Date | Cmpl Date | Owner
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42

## Schedule
ALL | Customer | C1 | CT | 2020-07-06 | 2020-07-07 | 2020-07-08 | 2020-07-09 | 2020-07-10 | 2020-07-11 | 2020-07-12 | 2020-07-13 | 2020-07-14 | 2020-07-15 | 2020-07-16 | 2020-07-17 | 2020-07-18 | 2020-07-19 | 2020-07-20 | 2020-07-21 | 2020-07-22 | 2020-07-23 | 2020-07-24 | 2020-07-25 | 2020-07-26 | 2020-07-27 | 2020-07-28 | 2020-07-29 | 2020-07-30 | 2020-07-31 | 2020-08-01 | 2020-08-02 | 2020-08-03 | 2020-08-04 | 2020-08-05 | 2020-08-06 | 2020-08-07 | 2020-08-08 | 2020-08-09 | 2020-08-10 | 2020-08-11 | 2020-08-12 | 2020-08-13 | 2020-08-14 | 2020-08-15 | 2020-08-16 | 2020-08-17 | 2020-08-18 | 2020-08-19 | 2020-08-20 | 2020-08-21 | 2020-08-22 | 2020-08-23 | 2020-08-24 | 2020-08-25 | 2020-08-26 | 2020-08-27 | 2020-08-28 | 2020-08-29 | 2020-08-30 | 2020-08-31 | 2020-09-01 | 2020-09-02 | 2020-09-03 | 2020-09-04 | 2020-09-05 | 2020-09-06 | 2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-12 | 2020-09-13 | 2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18 | 2020-09-19 | 2020-09-20 | 2020-09-21 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-26 | 2020-09-27 | 2020-09-28 | 2020-09-29 | 2020-09-30 | 2020-10-01 | 2020-10-02 | 2020-10-03 | 2020-10-04 | 2020-10-05 | 2020-10-06 | 2020-10-07 | 2020-10-08 | 2020-10-09 | 2020-10-10 | 2020-10-11 | 2020-10-12 | 2020-10-13 | 2020-10-14 | 2020-10-15 | 2020-10-16 | 2020-10-17 | 2020-10-18 | 2020-10-19 | 2020-10-20 | 2020-10-21 | 2020-10-22 | 2020-10-23 | 2020-10-24 | 2020-10-25 | 2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-10-29 | 2020-10-30 | 2020-10-31 | 2020-11-01 | 2020-11-02 | 2020-11-03 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-07 | 2020-11-08 | 2020-11-09 | 2020-11-10 | 2020-11-11 | 2020-11-12 | 2020-11-13 | 2020-11-14 | 2020-11-15 | 2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-11-20 | 2020-11-21 | 2020-11-22 | 2020-11-23 | 2020-11-24 | 2020-11-25 | 2020-11-26 | 2020-11-27 | 2020-11-28 | 2020-11-29 | 2020-11-30 | 2020-12-01 | 2020-12-02 | 2020-12-03 | 2020-12-04 | 2020-12-05 | 2020-12-06 | 2020-12-07 | 2020-12-08 | 2020-12-09 | 2020-12-10 | 2020-12-11 | 2020-12-12 | 2020-12-13 | 2020-12-14 | 2020-12-15 | 2020-12-16 | 2020-12-17 | 2020-12-18 | 2020-12-19 | 2020-12-20 | 2020-12-21 | 2020-12-22 | 2020-12-23 | 2020-12-24 | 2020-12-25 | 2020-12-26 | 2020-12-27 | 2020-12-28 | 2020-12-29 | 2020-12-30 | 2020-12-31 | 2021-01-01 | 2021-01-02 | 2021-01-03 | 2021-01-04 | 2021-01-05 | 2021-01-06 | 2021-01-07 | 2021-01-08 | 2021-01-09 | 2021-01-10 | 2021-01-11 | 2021-01-12 | 2021-01-13 | 2021-01-14 | 2021-01-15 | 2021-01-16 | 2021-01-17 | 2021-01-18 | 2021-01-19 | 2021-01-20 | 2021-01-21 | 2021-01-22 | 2021-01-23 | 2021-01-24 | 2021-01-25 | 2021-01-26 | 2021-01-27 | 2021-01-28 | 2021-01-29 | 2021-01-30 | 2021-01-31 | 2021-02-01 | 2021-02-02 | 2021-02-03 | 2021-02-04 | 2021-02-05 | 2021-02-06
Resource Planning | [54 empty] | Dan PTO | [105 empty] | TechLead PTO
[14 empty] | Tif | [6 empty] | Mark H
Platform Integration | Requirements Gathering / Design - Platform Integration and reports | [6 empty] | Requirements/Design |  |  |  |  | Requirements/Design | [5 empty] | Requirements/Design | [5 empty] | Requirements/Design | [6 empty] | Author BRD |  | Deliver BRD | [81 empty] | Approve BRD
| Custom Development | [114 empty] | Build Story | Dev | [6 empty] | Dev | [6 empty] | Dev Testing | [6 empty] | Dev
| Custom Development | [115 empty] | Customer dev | [6 empty] | Customer dev | [6 empty] | Customer dev testing | [6 empty] | Customer dev
| Build and Integrate | [129 empty] | Build/Integrate
| Implement Design | [142 empty] | Demo/UAT Handoff
| UAT/Training prep | [128 empty] | UAT / Training Prep | [6 empty] | UAT / Training Prep | [10 empty] | Training Prep
| UAT and issue resolution - Platform integration | [143 empty] | UAT |  |  | UAT |  |  |  |  | UAT approve
| Knowledge Transfer | [142 empty] | Agent
| User Training - Platform integration | [151 empty] | Awareness
| Go-Live Prep | [144 empty] | Go Live Prep |  |  |  |  | Go Live Prep | [6 empty] | Go/No
Go-Live - Platform integration
Post Go-Live Support
| Project Kickoff Meeting | 2020-07-07
| Initial Project Plan Delivery | 2020-07-14
| Business Requirements Design (BRD) - Phase 1 | 2020-07-15
| Complete Client Environment Pre-Requisites | 2020-07-17
| Business Requirements Design (BRD) - Phase 1 Signoff | 2020-07-24
| Elite Configuration | 2020-07-31
| Coding - Phase 1 | 2020-08-10
| Solution Demo based on BRD - Phase 1 | 2020-08-11
| UAT Acceptance - Phase 1 | 2020-08-17
| Training Phase 1 | 2020-08-24
| Go-Live Phase 1 | 2020-08-25
| Business Requirements Design (BRD) - Phase 2 | 2020-08-05
| Business Requirements Design (BRD) - Phase 2 Signoff | 2020-08-07
| Coding - Phase 2 | 2020-09-07
| Solution Demo based on BRD - Phase 2 | 2020-09-10
| UAT Acceptance - Phase 2 | 2020-09-14
| Training Phase 2 | 2020-09-24
| Go-Live Phase 2 | 2020-09-25
| Project Closeout | 2020-09-30
Timeline under review
Note on DN7: Tiffany Jansen: Polaris web service Ability to cache metadata (ANI, Agent ID, UCID) Invoking CTS web service to send metadata (User ID, Member ID, etc, to CTS db) Trigger event for pulling metadata into Polaris record

## OVA Links (hidden)
Updated as of 12/12/17
VMWare 5.5 - CT Comm Server SIP (for ESX 5.5).ova
https://www.dropbox.com/s/ekrn2ptntfh6lpi/CT%20Comm%20Server%20SIP%20%28for%20ESX%205.5%29.ova?dl=0
VMWare 6.0 - CT Comm Server SIP.ova
https://www.dropbox.com/s/9si726wlodv119i/CT%20Comm%20Server%20SIP.ova?dl=0
CT Suite - Deploy CT Comm OVA.pdf
https://www.dropbox.com/s/evqcju5do8mkhfp/CT%20Suite%20-%20Deploy%20CT%20Comm%20OVA.pdf?dl=0