## Slide 1
2019
2019
Today
Feb
Mar
Apr
May
Jun
Jul
Aug
Feb 1 - Mar 1
21 days
Planning
Mar 15 - May 1
34 days
Tech Health Servers
May 1 - Jul 1
44 days
Harbor App Servers
May 1 - Jul 15
54 days
Harbor SQL Servers
Apr 1 - Jul 1
66 days
Three File Servers
Jul 1 - Aug 1
24 days
Unlock Portal
Jul 15 - Aug 1
14 days
Domain Controllers
Jul 20 - Aug 1
9 days
Decommissioning
Abra process

## Slide 2
2019
2019
Today
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Apr 15 - May 1
13 days
Planning
Jun 1 - Jun 15
10 days
Build 2019 Test Servers (20)
Jul 1 - Aug 1
24 days
Upgrade 2008 Prod Servers
Jun 1 - Jul 1
21 days
Upgrade SQL Lower
Jul 15 - Aug 15
24 days
Upgrade SQL Prod
Sep 1 - Oct 1
22 days
Build App Servers DC4
Jul 1 - Aug 1
24 days
Upgrade Align-File to 2016 OS
Aug 15 - Sep 1
12 days
Set up HA node in dc4
Aug 15 - Sep 1
12 days
Set up secondary HA ndoe in DC4
Sep 1 - Oct 30
43 days
Replicate Fileshares to Azure
Oct 1 - Oct 15
11 days
Build Secondary nodes in DC4
Oct 15 - Oct 30
12 days
Replicate portion to DC4
Sep 15 - Oct 1
12 days
Build DC4 Align Domain Controllers
Nov 4 - Nov 15
10 days
UAT Testing in DC4
Nov 1 - Nov 15
11 days
Great Plains Replacement
Oct 1 - Oct 31
23 days
Script DNS Updates
1 day
Nov 27
Provision CRM
1 day
Nov 28
Provision Great Plains
1 day
Dec 6
Run DNS Update
1 day
Dec 6
Switch Primary DB to DC4
1 day
Dec 6
ReRoute FTP Traffic
Dec 11 - Dec 31
15 days
Decommission Hardware CSX
Cubic