## CoZy Risk Register
Risk Register
Risk ID | Aspects | Date Raised | Influence | Probability | Influence Description | Mitigation measures | Ownership | Status | Last Review Date | Date closed
1 | Fundings
1.1 | Funding shortfall to complete planned scope of work | 2021-06-01 | H | H | Project delays Reduced quality or scope Increased project risks Impact on stakeholder confidence Limitations in resource allocation Adverse financial consequences | Alternative funding bid currently being pursued with different sponsor | Project Management | Ongoing | 2021-07-01
1.2 | Major Business Case schema is not funded completely by sponsor | 27/2/2019 | H | H | Project delays or stalled progress Incomplete implementation Impacted project objectives Reduced benefits and ROI Stakeholder disappointment or dissatisfaction Uncertainty for project sustainability | Reduced scope scheme and look to secure additional funds | Project Sponsor | Ongoing | 2021-06-01
1.3 | No contract placed with outsource company to achieve program requirements and the possibility of losing developer agreements | 2021-05-01 | H | H | Delayed project execution Incomplete program requirements Uncertain resource availability Potential loss of developer agreements Legal and financial risks Impacted stakeholder relationships | Make sure that developer agreements and capital receipts have a sufficient timescale flexibility following completion of the planning and initiation stage | Project Management | Ongoing | 2021-06-01
2 | Marketing and management
2.1 | Poor ability of network marketing integration | 2021-06-01 | M | M | Inefficient communication Inconsistent brand messaging Missed target audience Decreased conversion rates Limited cross-selling and up-selling Diminished return on investment (ROI) | Plan additional marketing events and marketing budget | Marketing Manager | Ongoing | 2021-08-01
2.2 | High expenses of network marketing | 2021-08-01 | H | M | Increased financial burden Reduced profit margins Resource allocation challenges Increased financial risk | Rework marketing budget, get alignment on marketing with additional sponsors | Marketing Manager | Ongoing | 2021-08-09
2.3 | The lack of internal and external trends analysis | 27/2/2019 | M | M | Missed opportunities Ineffective strategic planning Reduced adaptability | Make proper inquisitions of representatives of involved markets, benchmarking | Marketing Manager | Ongoing | 2021-06-01
2.4 | The lack of e-business executives support and cooperation | 2020-05-04 | H | H | Hindered implementation Limited strategic alignment Impaired decision-making Slow adoption of digital transformation Inadequate resource allocation Missed innovation and growth opportunities | Strategy to involve executives and sponsors early on the discovery phase, demonstrating MVP of possible improvements | Delivery Management | Ongoing | 2021-06-02
2.5 | The lack of awareness of e-business executives | 2020-05-04 | H | H | Limited understanding of e-business Inadequate integration of e-business Missed competitive advantage Inefficient resource allocation Limited innovation and adaptability Reduced collaboration and alignment | Strategy to involve executives and sponsors early on the discovery phase, demonstrating MVP of possible improvements | Delivery Management | Ongoing | 2021-06-03
3 | Phisical store acquisitions
3.1 | Failure to negotiate land lease | 2020-05-04 | H | L | Delayed project start Increased costs Uncertainty in project scope Legal and regulatory challenges Damaged stakeholder relationships Reputational damage | Ongoing negotiations taking place right up to due date to resuce the number of objectors. Alternative plan and location are included into strategic budget planning | Project Manager | Ongoing, alternative options being considered | 2021-06-01
3.2 | Land requirements insufficient to accommodate agreed scheme | 2020-05-04 | L | L | Space constraints Reduced functionality Increased costs Potential delays Stakeholder dissatisfaction Revisions to project scope | Sufficient design work was undertaken at the outline design stage to ensure adequate land take identified for proposals. Changes to design layout kept to an absolute minimum thereafter | Project Manager | Ongoing | 2021-06-02
4 | Website maintanence
4.1 | Background system is not perfect and might be deprecated | 2021-08-01 | H | M | System limitations Risk of deprecation Compatibility issues Increased maintenance effort Limited support and resources Impact on business continuity | Constantly reassess the risk management strategies to ensure the website is reliable. Make sure that a continuous monitoring and patch management system is in place. | Solution Architect | Ongoing | 2021-09-01
4.2 | Backgroung system docking with web-stores and phisical shops is outdated and cannot support load | 2021-06-01 | H | M | Outdated integration Inadequate load support Performance issues Risk of data loss Business disruptions Competitive disadvantage | Consider internal monitoring, which is done behind the corporate firewall and works within the system, to keep the load fully operational | Solution Architect | Ongoing | 2021-06-01
4.3 | Website designs are not user-friendly and crushes often | 2021-06-01 | M | M | Poor user experience High bounce rates Negative brand perception Decreased customer satisfaction Loss of potential customers Technical maintenance burden | Use agile techniques to help solve these issues early on. | UI/UX Lead | Ongoing | 2021-06-01
4.4 | Website has not been optimized | 2021-06-01 | L | L | Slow page loading Lower search engine rankings Decreased conversion rates Inconsistent user experience Missed mobile opportunities Technical vulnerabilities | Set the right Key Performance Indicators (KPIs) to gauge whether system is effective enough. | UI/UX Lead | Ongoing | 2021-06-01
5 | Design management
5.1 | Failure to meet agreed programme milestones for design delivery before and during the approval period | 2021-06-01 | H | M | Delayed design approval Extended project duration Increased project costs Disrupted coordination with stakeholders Impact on project phases Reputational damage | Close liaison maintained between designers and project management to ensure delivery on programme | Project Manager | Ongoing | 2021-06-01
5.2 | Failure to agree responsibility for Interface boundaries with developers | 2021-08-02 | H | H | Communication issues Integration challenges Inefficiencies in development Quality issues Project delays Increased project costs | Coordination to be discussed through regular team meetings and requirements are understood | Delivery Manager | Ongoing | 2021-06-01
6 | Cost management
6.1 | Inaccurate Cost Plan estimates - base rates wrong, fluctuations, errors in take off, inadequacy of design detail | 27/2/2019 | H | L | Base rate inaccuracy Fluctuations in costs Errors in take-off Inadequate design detail Cost overruns Financial risks | Benchmarking exercise to be undertaken to check base rates. Regular dialogue between Cost Managers and Design team to confirm any initial assumptions | Delivery Manager | Benchmarking is being reviewed | 2021-06-01
6.2 | Full affect of changes not taken into account | 27/2/2019 | M | L | Scope creep Resource constraints Cost overruns Schedule delays Quality compromises Stakeholder dissatisfaction | Regular agenda item on team meetings to review any changes | Project Manager | Quality system now in place | 2021-06-01
7 | Partner integrations and Statury limitations
7.2 | Uncharted and unknown services | 27/2/2019 | H | M | Uncertainty Complexity Lack of benchmarking Higher risk of failure Potential cost overruns Need for specialized expertise | Coordination meetings held to ensure compatibility and requirements agreement | Project Manager | Meetings held with partners to ensure constant communication | 2021-06-01
7.3 | Insufficient access to partner software endpoints | 25/28/2020 | H | L | Integration challenges Limited functionality Data inconsistencies Workflow disruptions Delays in information exchange Missed business opportunities | Coordination meetings held to ensure compatibility and requirements agreement | Solution Architect | Ongoing | 2021-06-01
7.4 | Lack of availability to review and approve partners work | 25/28/2020 | M | L | Delays in project progress Reduced collaboration Missed milestones Quality risks Strained partner relationships Increased rework | Get involved into review process as early as possible, cooperating with partners, revising updates and documentation, managing constant communication | Solution Architect | Ongoing | 2021-06-01
9 | Security risk
9.1 | Lack of security upkeep | 27/2/2019 | H | M | Vulnerability exploitation Data loss or theft Compliance issues Disruption of operations Damage to reputation Increased costs | Invest in expensive countermeasures to additionally secure systems | Solution Architect | Ongoing | 2021-06-01
9.2 | Complex distribution process | 27/2/2019 | H | L | Operational challenges Increased risk of errors Longer lead times Higher costs Customer dissatisfaction Supply chain disruptions | Cybersecurity insurance | Solution Architect | Ongoing | 2021-06-01
9.4 | Lack of sufficient backups | 27/2/2019 | H | M | Data loss risk Recovery challenges Compliance and legal risks Impact on business continuity Reputational damage Cost of data recovery | Implement 3-2-1 backup strategy | Solution Architect | Ongoing | 2021-06-01